## PRODUCT BACKLOG EXAMPLE
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Home Member | register myself into the application using database | I can login into the System.
1 | SB1/US2 | Home Member | login into the system using my username & password | I can control my home remotely from anywhere.
1 | SB1/US3 | Home Member | create guest account into the database | I can add guests to the system.
1 | SB1/US4 | Home Member | go to profile page | I can add or update my profile details.
1 | SB1/US5 | Home Member | see all the users information | I came to know who can access my house.
1 | SB1/US6 | Home Member | change my password | password is updated.
1 | SB1/US7 | Home Member | go to delete users page | I can delete guest user/users if necessary.
1 | SB1/US8 | Home Member | press a button showing in the application | I can turn on the appliances.
1 | SB1/US9 | Home Member | press a button showing in the application | I can turn off the appliances.
1 | SB1/US10 | Home Member | get notified | I can understand that appliances are trurned on now.
1 | SB1/US11 | Home Member | get notified | I can understand that appliances are trurned off now.
1 | SB1/US12 | Home Member | turn on lights or lamps | lights or lamps gets turned on.
1 | SB1/US13 | Home Member | turn off lights or lamps | lights or lamps gets turned off.
1 | SB1/US14 | Home Member | increase the intensity of lights and lamps | I can use more brighter lights or lamps.
1 | SB1/US15 | Home Member | decrease the intensity of lights or lamps | I can dim lights or lamps.
1 | SB1/US16 | Home Member | turn on music player | I can listen to my favorite music any time.
1 | SB1/US17 | Home Member | turn off music player | music player gets turned off.
1 | SB1/US18 | Home Member | turn on fan | fan will be powered on.
1 | SB1/US19 | Home Member | turn off fan | fan will be powered off.
2 | SB2/US1 | Home Member | turn on lights/lamp using IR remote | in case of non availablity of internet connection
2 | SB2/US2 | Home Member | turn on fan using IR remote | in case of non availablity of internet connection
2 | SB2/US3 | Home Member | turn on music player using IR remote | in case of non availablity of internet connection
2 | SB2/US4 | Home Member | turn off lights/lamp using IR remote | in case of non availablity of internet connection
2 | SB2/US5 | Home Member | turn off fan using IR remote | in case of non availablity of internet connection
2 | SB2/US6 | Home Member | turn off music player using IR remote | in case of non availablity of internet connection
2 | SB2/US7 | Guest | go to request page of application | I make a request to any of the house member to register me.
2 | SB2/US8 | Guest | login into the system using my username & password | I will be able to access home remotely.
2 | SB2/US9 | Guest | go to my profile page | I can modify my details in the database.
2 | SB2/US10 | Guest | turn on lights or lamps | lights or lamps gets turned on.
2 | SB2/US11 | Guest | turn off lights or lamps | lights or lamps gets turned off.
2 | SB2/US12 | Guest | turn on fan | fan will be powered on.
2 | SB2/US13 | Guest | turn off fan | fan will be powered off.
2 | SB2/US14 | Guest | increase the intensity of lights and lamps | I can use more brighter lights or lamps.
2 | SB2/US15 | Guest | decrease the intensity of lights or lamps | I can dim lights or lamps.
2 | SB2/US16 | Guest | turn on music player | I can listen to my favorite music any time.
2 | SB2/US17 | Guest | turn off music player | music player gets turned off.
2 | SB2/US18 | Guest | turn on lights/lamp using IR remote | in case of non availablity of internet connection
2 | SB2/US19 | Guest | turn on fan using IR remote | in case of non availablity of internet connection
2 | SB2/US20 | Guest | turn on music player using IR remote | in case of non availablity of internet connection
2 | SB2/US21 | Guest | turn off lights/lamp using IR remote | in case of non availablity of internet connection
2 | SB2/US22 | Guest | turn off fan using IR remote | in case of non availablity of internet connection
2 | SB2/US23 | Guest | turn off music player using IR remote | in case of non availablity of internet connection
3 | SB3/US1 | Home Member | secure my home | only authenticated persons are allowed in the house.
3 | SB3/US2 | Home Member | control the openeing of my main door | no mannual work will be required to open the door.
3 | SB3/US3 | Home Member | control the closing of my main door | no mannual work will be required to close the door.
3 | SB3/US4 | Home Member | detect the guests who are arrival at my home | I come to know who is at my door.
3 | SB3/US5 | Home Member | decide whether to allow or deny this person | he/she can enter in my house.
4 | SB4/US1 | Home Member | customize my home ambience | I can set my home theme according to my mood.
4 | SB4/US2 | Home Member | get notified | I can turn on lights of my parking and garden area in evening.
4 | SB4/US3 | Home Member | get notified | I can turn off lights of my parking and garden area in evening.
4 | SB4/US4 | Home Member | get notified | I can not forget to switch off various appliances if I am out of my house.
4 | SB4/US5 | Home Member | get notified | I can turn on lights of my parking and garden area in evening.
4 | SB4/US6 | Home Member | get notified | I can not forget to switch off various lights after a certain time duration
4 | SB4/US7 | Home Member | set timer for geyser | I dont have to wait to turnon the geyser.
4 | SB4/US8 | Home Member | set timer for geyser | I dont have to wait to turnoff the geyser.
4 | SB4/US9 | Home Member | set timer for garden light | I dont have to wait to turnon the garden light.
4 | SB4/US10 | Home Member | set timer for garden light | I dont have to wait to turnoff the garden light.
US ID: <SB#1>/<US#1>
AR-Ashish Ranjan

## SPRINT BACKLOG EXAMPLE
SPRINT BACKLOG
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Making Robot>
SB1/D1 | Register into application | SB1/D1/T1 | Study of Android Application
|  | SB1/D1/T2 | Designing of GUI
|  | SB1/D1/T3 | Connecting application with database
|  | SB1/D1/T4 | Validating User Inputs and Implementaion of Pop up window
|  | SB1/D1/T5 | Implementation of Splash Screen
|  | SB1/D1/T5 | Testing of module
SB1/D2 | Login into the System | SB1/D2/T1 | Creating GUI of Login Window
|  | SB1/D2/T2 | Validating User Inputs
|  | SB1/D2/T3 | Implementation of intent in activity
|  | SB1/D2/T4 | Implementation of pop up windows
|  | SB1/D1/T6 | Testing of module
SB1/D3 | Create Web Service | SB1/D3/T1 | Study of RESTFUL Web Service
|  | SB1/D3/T2 | Creating a demo web Service
|  | SB1/D3/T3 | Taking request from application and giving response
|  | SB1/D3/T4 | Connecting web service with database
SB1/D4 | Go to profile Page | SB1/D4/T1 | Opening of a new activity using intent
|  | SB1/D4/T2 | Fetching user information from database
|  | SB1/D4/T3 | Updating information from database
SB1/D5 | See all users information | SB1/D5/T1 | Display user information from databse
SB1/D6 | Change Password | SB1/D6/T1 | Validating current password
|  | SB1/D6/T2 | verifying current password
|  | SB1/D6/T3 | Updating current password
|  | SB1/D6/T4 | showing pop up window of updation
SB1/D7 | Go to Delete Users Page | SB1/D7/T1 | Showing User Details Page
|  | SB1/D7/T2 | Deleting User details
|  | SB1/D7/T3 | Updating User details
SB1/D8 | Press a Button showing in the Application | SB1/D8/T1 | Create buttons of turn on/turn off
|  | SB1/D8/T2 | Implementing action listener on buttons
|  | SB1/D8/T3 | passing response from application
|  | SB1/D8/T4 | Testing of module
SB1/D9 | Get notified | SB1/D9/T1 | Web service function call on request
|  | SB1/D9/T2 | Passing request in the form of notification
SB1/D10 | Turn on lights/Lamp | SB1/D10/T1 | Simulation on proteus
|  | SB1/D10/T2 | connectivity of web service to hardware
|  | SB1/D10/T3 | implementation of serial port communication
|  | SB1/D10/T4 | Passing Instructions from Web service
|  | SB1/D10/T5 | Test connections firstly using virtual port and then physically
SB1/D11 | Turn off Lights/lamp | SB1/D11/T1 | Simulation on proteus
|  | SB1/D11/T2 | connectivity of web service to hardware
|  | SB1/D11/T3 | implementation of serial port communication
|  | SB1/D11/T4 | Passing Instructions from Web service
|  | SB1/D11/T5 | Test connections firstly using virtual port and then physically
SB1/D12 | Turn on Music Player | SB1/D12/T1 | Simulation on proteus
|  | SB1/D12/T2 | connectivity of web service to hardware
|  | SB1/D12/T3 | implementation of serial port communication
|  | SB1/D12/T4 | Passing Instructions from Web service
|  | SB1/D12/T5 | Test connections firstly using virtual port and then physically
SB1/D13 | Turn off Music Player | SB1/D13/T1 | Simulation on proteus
|  | SB1/D13/T2 | connectivity of web service to hardware
|  | SB1/D13/T3 | implementation of serial port communication
|  | SB1/D13/T4 | Passing Instructions from Web service
|  | SB1/D13/T5 | Test connections firstly using virtual port and then physically
SB1/D14 | Turn on Fan | SB1/D14/T1 | Simulation on proteus
|  | SB1/D14/T2 | connectivity of web service to hardware
|  | SB1/D14/T3 | implementation of serial port communication
|  | SB1/D14/T4 | Passing Instructions from Web service
|  | SB1/D14/T5 | Test connections firstly using virtual port and then physically
SB1/D15 | Turn off Fan | SB1/D15/T1 | Simulation on proteus
|  | SB1/D15/T2 | connectivity of web service to hardware
|  | SB1/D15/T3 | implementation of serial port communication
|  | SB1/D15/T4 | Passing Instructions from Web service
|  | SB1/D15/T5 | Test connections firstly using virtual port and then physically
SB1/D16 | Temprature Sensing | SB1/D16/T1 | Study of NTC temprature sensor
|  | SB1/D16/T2 | Simulation on proteus
|  | SB1/D16/T3 | implementation through virtual port
|  | SB1/D16/T4 | implementaion on temprature sensor
|  | SB1/D16/T5 | Passing the temprature sensed to application via web service
|  | SB1/D16/T6 | Testing of module
MP:Manasvi Patel

## SPRINT BACKLOG HOURS FOTMAT
SPRINT BACKLOG
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | DATE HOURS LEFT
SPRINT 1 - <NAME>
Task ID: <SB#1>/<US#1>/<Task#1>
GM-Gagan Mathur,KK-Karishma Kapoor,MP-Manasvi Patel,AR-Ashish Ranjan

## SPRINT BACKLOG HOURS EXAMPLE
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
[5 empty] | Hours | 2014-01-14 | 2014-01-21 | 2014-01-28 | 2014-02-04 | 2014-02-13
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | PG | Progress | 8 | 6 | 4 | 0
|  | Search about components required | PK | Progress | 8 | 6 | 4 | 0
|  | Purchase component from Market | NG | Progress | 8 | 6 | 3 | 0
|  | Develop the hardware | PM | Progress | 8 | 6 | 3 | 0
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | PG | Progress | 6 | 4 | 2 | 0
|  | search paint application | PK | Progress | 6 | 4 | 2 | 0
|  | search video making application | NG | Progress | 6 | 4 | 3 | 1 | 0
|  | search audio recording applications | PM | Progress | 6 | 4 | 3 | 1 | 0
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | PG | Progress | 5 | 3 | 2 | 0
|  | Study tutorials | PK | Progress | 5 | 3 | 2 | 0
|  | start with Basics of c# | NG | Progress | 6 | 3 | 1 | 0
|  | start with Basics of c# | PM | Progress | 6 | 3 | 1 | 0
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c# | PG | Progress | 6 | 3 | 1 | 0
|  | start with Basics of c# | PK | Progress | 6 | 3 | 1 | 0
|  | coding of onscreen application | NG | Progress | 16 | 12 | 10 | 7 | 3 | 0
|  | coding of onscreen application | PM | Progress | 16 | 12 | 10 | 7 | 3 | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | PG | Progress | 16 | 10 | 8 | 4 | 2 | 0
|  | coding of onscreen application | PK | Progress | 16 | 10 | 8 | 4 | 2 | 0
|  | Debug the code | NG | Progress | 8 | 5 | 3 | 2 | 0
|  | Debug the code | PM | Progress | 8 | 5 | 3 | 2 | 0
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | PG | Incomplete | 6 | 3 | 2 | 1 | 0
|  | Implentation of application on virtual screen. | PK | Incomplete | 6 | 3 | 2 | 1 | 0
|  | Implentation of application on virtual screen. | NG | Incomplete | 6 | 3 | 2 | 1 | 0
|  | Implentation of application on virtual screen. | PM | Incomplete | 6 | 3 | 2 | 1 | 0
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | PG | Incomplete | 3 | 0
|  | Interface it with PC/laptop | PK | Incomplete | 3 | 1 | 0
|  | Switch on the projector and set the projected screen | NG | Incomplete | 2 | 0
|  | Interface it with PC/laptop | PM | Incomplete | 2 | 1 | 0
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | PG | Incomplete | 2 | 1 | 0
|  | Use different applications on the virtual screen | PK | Incomplete | 8 | 4 | 3 | 0
|  | Check the changes made at the virtual screen | NG | Incomplete | 8 | 3 | 3 | 2 | 0
|  | Checking if it is working effectively with the laptop and not damaged | PM | Incomplete | 3 | 2 | 1 | 0
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | PG | Incomplete | 8 | 4 | 2 | 0
|  | Prepare all software deliverables | PK | Incomplete | 8 | 4 | 2 | 0
|  | Prepare a hardware & software guide | NG | Incomplete | 8 | 5 | 3 | 0
|  | Prepare a user manual & guide for the users | PM | Incomplete | 8 | 3 | 2 | 0
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | PG | Incomplete | 8 | 5 | 3 | 1 | 0
|  | Project demonstration | PK | Incomplete | 5 | 3 | 0
|  | Project demonstration | NG | Incomplete | 5 | 3 | 0
|  | Project to be operated by different users | PM | Incomplete | 8 | 4 | 2 | 0
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## BURN DOWN CHART
Date | Desired Trend
2014-01-14 | 167
2014-01-21 | 103
2014-01-28 | 35
2014-02-04 | 10
2014-02-13 | 0
Tasks
Days

## PRODUCT BACKLOG FORMAT
Sr no. | BACKLOG ITEM |  |  | PRIORITY | ESTIMATION (In days)
| AS A/AN | I WANT TO | SO THAT
1 | Admin | Login | I can get admin's access. | 100 | 1
2 | Admin | Create users | user can ask for a room boooking | 95 | 1
3 | User | Login | So that I can authenticate account during login | 90 | 1
4 | Admin | add a new room with its specifications | users can conduct a training program | 85 | 2.5
5 | User | check availability of rooms with its specifications | I can ask for booking to admin. | 80 | 1.5
6 | Admin | check availability of rooms | I can confirm booking for a user. | 75 | 1.5
7 | User | raise request to book a room | I can send a request for it. | 70 | 1.5
8 | Admin | acknowledge respective user for cancellation or confirm booking | user canbe acknowledged. | 65 | 2.5
9 | Admin | Delete existing user,update | he can no longer ask for booking a room | 60 | 1.5
10 | Admin | maintain the status of rooms | I can keep users updated. | 55 | 1.5
11 | User | add my profile | admin and other users can go through it. | 50 | 1.5
12 | User | cancel my booking | it could be made available to other users. | 45 | 1
13 | Admin | Remove a new room and update | it can not be shown for availability | 40 | 2.5
14 | Admin | view history of previous bookings monthly and weekly | arrange the specifications. | 35 | 1
15 | User | view history of previous bookings monthly and weekly | arrange the specifications. | 30 | 1
| Total |  |  |  | 22.5

## SPRINT BACKLOG FORMAT
SPRINT BACKLOG
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Making Robot>